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Delaware Cancer Consortium
Early Detection & Prevention Committee
January 11, 2021
Minutes-APPROVED
Virtual Meeting




	
Members
	

	Did not participate
	Vikas Batra, MD, FACP, FC – Sussex Pulmonary & Endocrine Consultants, PA

	Participated
	Heather Bittner-Fagan, MD, MPH – Christiana Care Health System

	Did not participate
	Tiffany Edwards – Sussex County Health Coalition

	Participated
	Allison Gil, American Cancer Society

	Participated
	Stephen Grubbs, MD – American Society of Clinical Oncology

	Participated
	Sarah Hutton, EdD – Boys and Girls Club of Delaware

	Participated
	Nora Katurakes, RN, MSN, OCN – Christiana Care Health System 

	Did not participate
	Stephanie McClellan, MSN, RN, CMSRN – Bayhealth Medical Center

	Participated
	Lauren Moore, Tidal Health, Nanticoke

	Participated
	Sue Murray, DE Breast Cancer Coalition

	Participated
	Carolee Polek, RN, MSN, PhD – DE Diamond Chapter of the Oncology Nursing Society

	Did not participate
	Albert Rizzo, MD, FACP, FCCP – Christiana Care Health System

	Did not participate
	Robert Sikes, PhD. – University of Delaware

	Participated
	Sarah Toborowski – Quality Insights

	Did not participate
	Crystal Wright – Henrietta Johnson Medical Center

	Did not participate
	Michael R. Zaragoza, MD, FACS – Delaware Prostate Cancer Coalition

	
	

	Staff

	

	Participated
	Helen Arthur – Delaware Division of Public Health

	Participated
	Rosemary Doughten – Delaware Division of Public Health

	Participated
	Melissa Keiper – Delaware Division of Public Health

	
	

	Public/Guests
	

	Participated
	Suzanne Corson – Susan G. Komen

	Participated
	Robyn Biehm – Christiana Care Health System

	Participated
	Rita Williams – Beebe Healthcare

	Participated
	Lisa Gruss – Quality Insights

	
	


Welcome/Review/Approval of minutes



Review/Approval of Minutes
Chair, Dr. Heather Bittner-Fagan began the meeting at 10:05 am.  A motion was made by Dr. Stephen Grubbs to approve the October 2020 minutes and all participating approved the minutes as written.
Human papillomavirus (HPV) 5-year plan
Ms. Melissa Keiper, , Clinical Cancer Director, Division of Public Health (DPH) provided the HPV 5-year plan update for Mr. Jim Talbott, HPV Program Manager as he was unavailable due to working COVID-19 detail.  Ms. Keiper advised that headway is being made with the Department of Education (DOE) partnership, specifically increasing education on the importance of the HPV vaccine for boys and girls.  Regarding partnerships with insurance companies, some efforts have been stalled as a result of the pandemic.  Work is continuing with the State Innovation Committee and there is an ongoing contract with Quality Insights to increase providers’ knowledge and also to provide training regarding this initiative.  New media campaigns are waiting to be launched to be sure health care providers will be able to accommodate.  There was also an educational opportunity provided to the dental community.  Dr. Bittner-Fagan inquired if the HPV vaccine is routinely offered by school-based health centers.  One challenge identified at wellness centers includes lack of continuity of care, particularly since not all centers have access to Electronic Health Records (EHR).  Some wellness centers are still using a paper-based records system.  Additionally, parental consent is required for participation in wellness centers and can be a barrier to receiving care.  Additional barriers include form completion to receive the vaccine as well as are Medicaid and other insurance barriers.

Lung 5-year plan
Ms. Keiper provided an update of the Lung Cancer Screening Program 5-year plan.  The goals of the plan are:
	GOAL 1: Continue to promote lung cancer screening
	GOAL 2: Analyze Data in cancer screening databases
GOAL 3: Inform and educate health care providers and general public on available resources
	GOAL 4: Encourage healthy lifestyles and reduce risky behaviors
GOAL 5: Initiate and support policies and programs to reduce tobacco use and exposure to secondhand smoke
GOAL 6: Prevent initiation of tobacco, nicotine and emerging products use among youth and young adults
GOAL 7: Increase the number of Delawareans who stop using tobacco and nicotine products
Much discussion took place regarding how and what information is sent to the screening database.  It was suggested that a survey be created and sent to each lung cancer screening location to ask how information is gathered and what elements are missing.  Chair Dr. Bittner-Fagan asked Nora Katurakes to initiate an email to testing sites to inquire who is contact person and what is the clinical process for gathering information and submitting information, to ensure consistency in data elements that are submitted by all sites.  

Further discussion for Goal 2, #4 - Determine feasibility of developing and implementing a comprehensive cancer screening registry for Delaware.  Lung cancers should be reported to the American College of Radiology (ACR).  The Screening for Life Program continues to work with the ACR to determine reporting capabilities – warranted adding “revisit BRFSS guidelines now that the data has been released”.  Dr. Grubbs stated that data sets from both the ACR and BRFSS need to be continually analyzed. 

A question was posed as to how the DCC in collaboration with DPH would pay for additional patient navigators that are listed in Goal 1, #2 - Support Patient Navigators to support lung cancer screening.  Ms. Helen Arthur, Health Promotion Disease Prevention Section Chief, advised that there is no additional funding and that work is continuing with Delaware Hospital Association in gathering manpower to host patient navigation. Dr. Bittner-Fagan suggested removing part of the goal that aims to  look at additional resources to support nurse navigation.  Dr. Grubbs inquired if it is possible for Quality Insights to add additional sites for the health systems work, they are currently providing for lung cancer screening.  Ms. Sarah Toborowski from Quality Insights responded that they are recruiting five additional sites to increase lung cancer screening programs and rates.

DE Lung Cancer Screening Program
In 2015 the decision was made for the Screening for Life Program to reimburse providers for lung cancer screening for eligible clients. Originally the program provided screening for eligible clients for a duration of  three years.  In 2018 the Committee decided to extend the screening duration  for an additional two years for a total of five years.  At the end of the five-year period the data was to be reviewed.  Dr. Bittner-Fagan brought up the draft recommendations from United States Preventative Services Task Force (USPSTF).  Does the mortality benefit increase from the benefit of the program for 10 years?  There is benefit beyond five years.  Is there evidence to extend the screening for individuals to 10 years?  Dr. Grubbs stated that the data must be reviewed.  The recommendation for the top age limit is still 80 even if the program would allow lung cancer screening to continue.  This will be further discussed and finalized during the next committee meeting. 

Sharing Time
Ms. Suzanne Corson from Susan G. Komen shared information regarding the Komen Treatment Assistance Program.  It is available to all battling breast cancer that meet financial criteria.  The Program will be expanding in the next few months.  If anyone has any questions she can be contacted at scorson@komen.org and the website is https://www.s.komen.org/treatment-assistance-program/. 

Ms. Nora Katurakes from Christiana Care Health System inquired if the IMPACT group still meets.  She also requested information on the smoking quit rate and the number of people using the Quitline.  

Dr. Grubbs advised that the recommendations for colorectal cancer from the United States Preventative Services Task Force (USPSTF) are out for comment.  He thinks they are dropping the age to 45 but still waiting for the final recommendations.

Ms. Helen Arthur advised that the Cancer Risk Reduction committee received a presentation on flavored tobacco products during their meeting.  ED&P committee members were also interested in seeing the presentation.  It was proposed to offer it as a lunchtime presentation at the April 12, 2021 meeting.

Public Comment
No comments were made during this time.

Adjournment
The meeting was adjourned at 11:25 am.

Attachments



                               

Meeting documentation is available on the DCC website (www.healthydelaware.org) or by contacting Rosemary Doughten (Rosemary.Doughten@delaware.gov or 302-744-1000).
Future Meeting (s)




	Next Meeting:

Monday, April 12, 2021
Location - TBD

	Remaining 2021 meetings: 

Monday, July 12 
Monday, October 11 
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approved 7.9.18 HPV 5 year plan


Task/Actions
Responsible 
Party


Data Source Timeframe January 2021 Update


1 Form partnership with the Department of Education (DOE) to collaborate on 
increasing education on the importance of HPV vaccination for boys and girls.


DPH and DOE MOU
Year 1 and 
ongoing 


Ongoing. DPH attended the August 2020 DOE Nurses' 
meeting.  Discussed the School survey, converage rates 


and HPV updates and information.


2 Form partnership with the Department of Insurance (DOI) to collaborate with 
Insurance Providers to promote HPV Vaccinations to their medical providers.


DPH and DOI MOU
Year 1 and 
ongoing


Ongoing. Reached out to the Department of Insurance 
on 9/26/18 about Insurance providers promoting HPV 


vaccinations.


3
Work with the State Innovation Committees to add the HPV vaccine discussion and 
distribution metrics to the provider scorecard statewide to measure change. DPH


Provider 
scorecard


Year 1 and 
ongoing


Ongoing. Activity:  Reached out to Innovation Committee 
on 6/1/2018, was referred to Elizabeth Brown, reached 


out to her on 9/27/18.  


4
Provide training to medical providers on Quality Initiatives to increase providers 
knowledge on HPV vaccinations, communication techniques and vaccination coverage 
information to promote succssful administration of HPV vaccinations.


DPH Contract Year 1‐2
Ongoing: Initial contract completed on 6/30/18.  RFP has 
been awareded to Quality Insights‐ contract extended 


through 6/30/2022


5


Provide training on the use of the Immunization Information System in order to view 
and reconcile coverage rate data in the Immunization Information System for HPV 
vaccinations.


DPH Contract Years 1‐5  Ongoing: Contract is in place through 6/30/2022.


OBJECTIVE 2A: Conduct a multi‐pronged approach targeting parents and physicians about the importance of the HPV vaccine for cancer prevention. 


GOAL 2: Provide human papillomaviruses (HPV) vaccine to girls, young women, boys, and young men ages 9‐26. 
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approved 7.9.18 HPV 5 year plan


Task/Actions
Responsible 
Party


Data Source Timeframe January 2021 Update


OBJECTIVE 2A: Conduct a multi‐pronged approach targeting parents and physicians about the importance of the HPV vaccine for cancer prevention. 


GOAL 2: Provide human papillomaviruses (HPV) vaccine to girls, young women, boys, and young men ages 9‐26. 


6
Provide data entry services for providers to update their HPV vaccination data in the 
Immunization Information System to arrive at a accurate coverage rate for HPV.


DPH Contract Years 1‐5


Ongoing. A Request for proposal (RFP) has been 
submitted, but with only one bidder.  Bidder did not 
meet the requirements.  Program will be looking at 
alternative means of providing the service.  Due to 
pandemic, further efforts have been unable to be 


undertaken. 


7 Disseminate messages statewide using trackable media tactics to both parents and 
physicians on the importance of HPV vaccination for boys and girls ages 9‐26.


DPH and 
Contractor


Evaluation Years 1‐2
Ongoing.  Strategic plan to inform awareness, education, 
and outreach efforts are underway.  Plan to launch in 
Janaury 2019. Media campaign intitiated in 2019.


8
Conduct an evaluation of media tactics to determine the effectiveness, and refine as 
needed based on results.  DPH 


Trackable 
media 


Years 2‐3


Ongoing.  Evaluation conducted at the end of campaign 
period.  Using FB newsfeed ads, 41K people reached 


delivering 623 clicks and 477 website
visits.  The banner ads were very successful spreading
awareness, delivering over 2M impressions and over
5K clicks.  The banners drove 3,599 website sessions.


9
Provide workflow assessments to immunization providers to ensure correct 
recommendation of HPV at each office visit.   DPH Contract Year 2


Ongoing.  Program will reach out to determine feasibility 
of the assessment. Contract to conclude 6/30/2022
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approved 7.9.18 HPV 5 year plan


Task/Actions
Responsible 
Party


Data Source Timeframe January 2021 Update


OBJECTIVE 2A: Conduct a multi‐pronged approach targeting parents and physicians about the importance of the HPV vaccine for cancer prevention. 


GOAL 2: Provide human papillomaviruses (HPV) vaccine to girls, young women, boys, and young men ages 9‐26. 


10


Promote the HPV Vaccine is Cancer Prevention Champion Award program will serve 
to motivate clinicians to adopt effective recommendation practices, and help educate 
clinicians on the individual‐ and practice‐level changes that can improve HPV 
vaccination rates. The program also serves reinforcement for parental audiences that 
HPV vaccination is an important part of cancer prevention and a normal part of 
adolescent immunization.


DPH
Trackable 
website 


engagement
Year 2


1st Champion has been nominated, package e‐mailed to 
the CDC on 9/4/2018, nomination package went out to 


qualified providers in 2019 but no responses were 
submitted to the program. The program will continue to 
send out HPV Champion Information to eligible providers 


yearly.


11
Provide education opportunities to Dental community concerning HPV, to include 
screening, surveillance, and immunization. DPH Contract Year 2


Completed. Reached out to Dental Director and Dental 
Society of Delaware.  Research to determine educational 


needs of Dental community.


12
Evaluate the provider scorecard to determine effectiveness.


State 
Innovation 
Committee


Provider 
scorecard


Year 5
Ongoing. Activity:  Reached out to Innovation Committee 
on 6/1/2018, was referred to Elizabeth Brown, reached 


out to her on 9/27/18.  


13
Arrive at a consensus with Colleges and Universities on making HPV a 
recommended/required vaccination for college entry


DPH and 
Immunization 
Coalition of 
Delaware


Evaluation Years 2‐3


Completed: Reached out to Coalition on 9/19/18 to host 
meeting on vaccine recommendations for college entry 
with colleges and universities in Delaware. Kate Smith 
reached out to 2 Colleges and Universities. There was 
little interest from these colleges/universities to meet. 


No current activities due to COVID 19.
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approved 10‐8‐2018 Lung 5 year plan 


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1 Determine baseline number of late stage lung cancers diagnosed. DPH DCR Year 1 Done.   Out of 3,965 lung cancers diagnosed, 2942 (73.7%) are late stage (regional and distant combined).  847 are local, and 194 are unknown.


2 Support Patient Navigators to support lung cancer screening.
ED&P Committee and 
DPH Contracts Year 1


Ongoing.   Statewide lung navigators are in place at Christiana Care and Bayhealth.   Work is needed to determine if additional lung patient navigators 
are needed.  


3
Maintain current and establish new relationships with primary care providers to 
increase screening rates for Medicare patients. DPH and Navigators


Screening for Life 
Provider 
Agreement, 
Screening Rates Year 1‐5 Ongoing.   Agreements in place with 4 provider sites.  Aim to recruit up to three additional provider sites.   


4 Enhance relationships with Medicaid and FQHCs to increase screening rates. DPH Organization Data Year 1‐5 Ongoing.   Quality Insights is activly pursuing one FQHC to initiate Academic Detailing program for providers and patient navigators at this site. 


5
Increase the number of screenings performed in areas where late stage lung 
cancers are more predominately diagnosed. Navigators and DPH


Cancer Incidence 
and Mortality 
Data Year 1‐5 Ongoing.  Additional data analysis is needed to identify gaps and barriers in screening. 


6
Explore expanding lung cancer screenings to those with occupational exposure 
and/or those exposed to second hand smoke. DCC


National Lung 
Cancer Screening 
Guidelines Year 5


The US Preventive Services Task Force (USPSTF) issued draft guidelines July 2020.  Draft recommendations expand screening eligibility to include 
annual screening with low‐dose CT in adults ages 50 ‐ 80 who have a 20 pack year smoking history and who currently smoke or have quit smoking 
within the past 15 years.  This is a "B" recommendation.  Final determination of adaptation of these guidlines is pending a final decision by the USPSTF.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1
Continue annual allocation for lung cancer screening for men and women 
ineligible for federal funded screening. General Assembly State Budget


Year 1 and 
ongoing Ongoing.  


2
Reimburse providers through the Screening for Life program for services for lung 
cancer screening for men and women   DPH


State and Federal 
Budget


Year 1 and 
ongoing Ongoing.  


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1
Review data elements available in the Screening for Life Database and Delaware 
Lung Cancer Registry. DPH Database Year 1 Ongoing.  


2
Expand and modify current database used to track screening activity in the SFL 
program and update as necessary. DPH, Contractor Database


Year 2 and 
ongoing Done. New Screening for Life database was placed into production July, 2020.   


3
Evaluate screening data in both the SFL program and the Delaware Lung Cancer 
Registry. DPH Screening data


Year 1 and 
ongoing Ongoing.  


4
Determine feasibility of developing and implementing a comprehensive cancer 
screening registry for Delaware. ED&P Committee Year 5


Lung cancers should be reported to the American College of Radiology.  The Screening for Life program continues to work with the ACR to determine 
reporting capabilities.    


GOAL 1: Continue to promote lung cancer screening


GOAL 2: Analyze Data in cancer screening databases


GOAL 3: Inform and educate health care providers and general public on available resources.


OBJECTIVE 1A  Decrease the number of late stage lung cancer diagnoses by 20%


OBJECTIVE 1B: Reimburse lung cancer screening for Delawareans who meet age and income eligibility guidelines.


OBJECTIVE 2A: Review available data.
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approved 10‐8‐2018 Lung 5 year plan 


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1
Promote campaigns to public and businesses focusing on available resources.


DPH, Contractor Campaign
Year 1 and 
ongoing


Ongoing.  An analysis was recently performed to identify potential gaps in current marketing efforts.  This information will be used to inform new 
campaigns and marketing efforts.  Additional information is being gathered to determine effectiveness of screening campaign in light of on‐going 
pandemic. 


2
Provide updates to health care professionals through letters and personal 
outreach. DPH, Contractor Letters


Year 1 and 
ongoing


Ongoing.  Lung navigators conduct outreach to providers offices.  Updates are sent to providers via newsletters.  Academic detailing program will 
continue to be deployed to interested providers.   


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1 Increase awareness of available cessation programs and resources.


DHSS tobacco program 
staff, IMPACT members, 
DCC ATS, Quitline Ongoing


Ongoing. Print ads, radio ads and social media ads were developed to let individuals know that smokers are at an increased risk of severe illness from 
COVID‐19.  


2 Increase awareness of problems associated with secondhand smoke.


DHSS tobacco program 
staff, IMPACT members, 
DCC ATS, YTS, BRFSS Ongoing Ongoing.  Ongoing education on second hand smoke via television commercial and social media.


3


Use "counter‐marketing" to decrease the effectiveness of tobacco industry 
promotions and to increase knowledge of harmful effects of tobacco and nicotine 
use.


DHSS tobacco program 
staff, IMPACT members, 
DCC ATS, YTS Ongoing


Ongoing.  Print ads, radio ads and social media ads were developed to let people know that smokers are at an increased risk of severe illness from 
COVID‐19.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1


Increase the percentage of health care practioners (including ob‐gyns and 
pediatricians) who inquire about secondhand smoke exposure in homes and 
vehicles and who counsel patients and their families regarding the dangers of 
secondhand smoke.


DPH Tobacco program 
staff, IMPACT members, 
DCC


Physician Survey, 
BRFSS, ATS, YTS Ongoing


In the fall 2018, 28 home visitors were trained on home health hazards (including secondhand smoke) and cessation resources including the Delaware 
Quitline.


2


Develop partnerships with the Department of Education as well as various 
programs across DPH to increase awareness of the problems associated with 
secondhand smoke. 


DPH Tobacco Prevention 
Program, Maternal & 
Child Health, Health 
Equity and Northern and 
Southern Health Services  BRFSS, YTS


Year 1 and 
ongoing


Vape toolkit (vapefreede.com) was developed in partnership with DOE, Kids Department and Polytech. Toolkit includes downloadable fact sheets, 
curriculums, links to other resources(including smoke free policies and other education on secondhand smoke) and a social media calendar kit.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1


Disseminate information about the harmful effects of tobacco and vape smoke to 
consumers and vulnerable populations through targeted multimedia campaigns 
and community outreach.


DPH, Voluntary heath 
organizations


Media tracker, 
ATS, BRFSS Ongoing


Ongoing. A  commercial which informs the public that some vape pods can contain as much nicotine as a pack of cigarettes airs on television and social 
media outlets used by youth and young adults. Vape toolkit (vapefreede.com) was developed in partnership with DOE, Kids Department and Polytech. 
Toolkit includes downloadable fact sheets, curriculums, policies, links to other resources and a social media calendar kit.


2
Educate health practioners through professional associations on the value of 
preventing exposure to secondhand smoke, including vapor emissions.


DPH, Voluntary heath 
organizations, IMPACT Physician Survey Ongoing Ongoing


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1


Educate and inform legislators and decision makers on the health and economic 
benefits of increasing the state excise tax on tobacco products and having a tax 
on e‐cigarettes.


Voluntary health 
organizations, IMPACT, 
DCC


Legislation 
tracker Ongoing Ongoing


GOAL 4: Encourage healthy lifestyles and reduce risky behaviors


GOAL 5: Initiate and support policies and programs to reduce tobacco use and exposure to secondhand smoke.


OBJECTIVE 3A: Develop and implement evidence based education campaigns.   


OBJECTIVE 4A: Develop, implement and evaluate social marketing campaigns to support tobacco free living


OBJECTIVE 5A:  Increase excise tax on tobacco products.


OBJECTIVE 4B: Educate the public about ways to lower their cancer risks.


OBJECTIVE 4C: Increase the number of people who don't allow smoking in their homes or vehicles.
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2


Educate and inform the general public on the many health and economic benefits 
of increasing the state excise tax on tobacco products and having a tax on e‐
cigarettes.


Voluntary health 
organizations, IMPACT, 
DCC ATS Ongoing Ongoing


3 Introduce and pass legislation to increase the excise tax on tobacco products.
Voluntary health 
organizations, legislature


Legislation 
tracker Ongoing Excise tax was increased in 2017.


4 Introduce and pass legislation to tax e‐cigarettes.
Voluntary health 
organizations, legislature


Legislation 
tracker Ongoing E‐cigarettes have been taxed since 2017.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1 Monitor draft legislation for any potential changes to CIAA.


Voluntary health 
organizations, IMPACT, 
DCC, DHSS


Legislation 
tracker Ongoing


Ongoing. Senate Substitute 1 for Senate Bill 25, was passed and raised the age of sale of tobacco products to 21 years (effective July 16, 2019). It also 
amended the CIAA to prohibit individuals under 21 from entering vapor establishments.


2 Enforce laws pertaining to secondhand smoke from vape products. DPH CIAA log Ongoing Ongoing. DPH created new signs for vapor establishments to post regarding the change in law that individuals under 21 are not allowed to enter.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1
Work with public (Medicaid) and private insurance, unions and employers to 
cover cessation counseling and products.


Voluntary health 
organizations, IMPACT, 
DCC, DHSS


Quitline, ATS, 
Insurance plan 
data Ongoing Ongoing. Medicaid currently reimburses DPH partially for Medicaid clients that use the Quitline.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1
Work with public (Medicaid) and private insurance, unions and employers to 
cover cessation counseling and products.


Voluntary health 
organizations, IMPACT, 
DCC, DHSS


Insurance 
records, ATS Ongoing Ongoing. Medicaid currently reimburses DPH partially for Medicaid clients that use the Quitline.


2
Continue to recommend funding from Delaware Health Fund for tobacco 
prevention activities. DCC, IMPACT


DHFAC 
recommendation Annually The DHFAC recommended level funding for tobacco prevention activities for FY22.


3
Identify potential funding opportunities to support tobacco prevention efforts 
from private and federal sources. DHSS, IMPACT


Total amount of 
funding Ongoing Ongoing


4
Enact legislation to increase the age to 21 to purchase cigarettes and other 
tobacco products.


Voluntary health 
organizations, legislature


Legislation 
tracker Year 2 Legislation (Senate Substitute 1 for Senate Bill 25) was introduced and passed  that increased the age of sale to 21. This went into effect July 16, 2019.


5 Increase the cost of retail business license to sell tobacco from the current $5.
Voluntary health 
organizations, legislature


Legislation 
tracker


Year 2 and 
ongoing HB242 was passed in 2017. This raised the cost of license to $50 (including vape store owners).


6 Enact legislation to require vapor establishments to have tobacco sale licenses.
Voluntary health 
organizations, legislature


Legislation 
tracker


Year 2 and 
ongoing HB242 was passed in 2017. Vapor establishments are now required to have tobacco retailer licenses.


7
Support development of policies by agencies who are responsible for individuals 
under their jurisdiction.


Voluntary health 
organizations, IMPACT, 
DCC, DHSS Survey data Ongoing Ongoing


8
Provide tobacco plan to agencies and organizations and partner with them to 
achieve objectives. DHSS, IMPACT, DCC Program records Ongoing Ongoing


9 Review and update Tobacco Plan IMPACT, DHSS Program records Year 1 The tobacco plan was updated in 2017.  The next update is planned for 2022.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


OBJECTIVE 5B: Sustain and enforce Delaware's Clean Indoor Air Act (CIAA)


OBJECTIVE 5C: Increase insurance coverage for cessation.


OBJECTIVE 5E: Reduce exposure to secondhand smoke in outdoor areas.


OBJECTIVE 5D: Support National and Delaware tobacco policy initiatives.
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1
Support development of policies to not allow smoking near entrances or exits to 
buildings.


Voluntary health 
organizations, IMPACT, 
DCC, DHSS


Program records, 
mini grants Ongoing Ongoing


2
Support health care facilities, workplaces, agencies and municipalities to develop 
smoke‐free grounds policies.


Voluntary health 
organizations, IMPACT, 
DCC, DHSS Survey data Ongoing Ongoing. Through mini grants have provided support for municipalities as they go smoke free. Includes providing funds for signage.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1
Identify new locations, including multi‐housing units that will adopt no‐smoking 
policies.


Voluntary health 
organizations, IMPACT Survey data Ongoing Ongoing


2


Increase the percentage of health care practitioners who inquire about 
secondhand smoke exposure in homes and who counsel patients and their 
families.


Voluntary health 
organizations, IMPACT, 
DCC, DHSS


Survey data, 
provider 
scorecard Ongoing Ongoing provider education.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1
Implement evidence‐based tobacco prevention programs for schools and 
communities.


DHSS tobacco program 
staff, IMPACT members, 


Program records, 
YTS Ongoing


Ongoing provision of mini grants and funding of youth led activities such as Kick Butts Generation.  DPH has assisted some schools with implementing 
Botvin Lifeskills curriculum which includes traditional tobacco use prevention as well as e‐cigarettes.


2 Conduct programs in colleges and workplaces that target young adults.
DHSS tobacco program 
staff, IMPACT members Program records Ongoing Ongoing. Delawareans Against Nicotine and Tobacco Exposure is a coalition of young adults active on various college campuses in Delaware.


3


Enforce Delaware tobacco Regulation 877, which prohibits the use and 
distribution of tobacco products by all staff, students, visitors and parents in 
school buildings, on school grounds in school leased or owned vehicles and 
property and all school affiliated functions, on and off school grounds. DOE, IMPACT members


School profile 
reports 
(violations 
recorded) Ongoing Ongoing


4 Ensure evaluation is conducted on all programs and activities.


DCC, Voluntary health 
organizations, DPH 
Cancer Program


Surveys, focus 
groups, trackable 
media


Year 1 and 
ongoing


Ongoing‐ Youth Tobacco Survey, focus groups etc. American Lung Activities (Kick Butts Generation/FORCE, DANTE) are evaluated by a subcontract 
Public Health Management Consultants.


Task/Actions Responsible Party Data Source Timeframe January 2021 Update


1 Provide qualified counseling services (Quitline/face‐to‐face).
DPH tobacco program 
staff Quitline  Ongoing


Ongoing.  During Fiscal Year 2020, the Delaware QuitLine received 7434 calls with 2108 individuals receiving cessation counseling by phone and 571 
registrants to receive face‐to‐face counseling.  


2 Provide online information and resources.
DPH tobacco program 
staff


Quitline, web 
reports Ongoing


Ongoing. Coaching provided through QuitSupport.com. Information also provided at HealthyDelaware.org. The new online vape tool kit will include 
resources for quitting vaping.


3 Provide approved cessation products to program recipients.
DPH tobacco program 
staff Quitline  Ongoing Ongoing‐ Quitline provides all seven FDA approved cessation aids free of charge to participants.


GOAL 6: Prevent initiation of tobacco, nicotine and emerging products use among youth and young adults.


GOAL 7: Increase the amount of Delawareans who stop using tobacco and nicotine products.


OBJECTIVE 6A: Fund youth and young adult tobacco prevention programs.


OBJECTIVE 7A: Enhance available resources to help people quit use of tobacco and nicotine products.


OBJECTIVE 5F: Explore potential policies to reduce children’s exposure to secondhand smoke.
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4 Ensure evaluation is conducted on all programs and activities.


DCC, Voluntary health 
organizations, DPH 
Cancer Program


Surveys, focus 
groups, trackable 
media, Quitline


Year 1 and 
ongoing Ongoing: Adult Tobacco Survey, Quitline participant survey postcard, Quit rates (@34%).


Task/Actions Responsible Party Data Source Timeframe January 2021 Update
1 Provide cessation programs specific to youth and young adults. DPH tobacco program  ATS, YTS Ongoing Ongoing. Not on Tobacco Use (NOT) has been enhanced to include e‐cigarettes. 


2 Expand current programs to include youth.
DPH tobacco program 
staff YTS Ongoing


The Delaware Quitline lowered age requirements to allow those under age 18 to use services. Indviduals aged 13 ‐ 17 are able to utilize the Quitline's 
phone counseling and online services. This change went into effect in November, 2019.


OBJECTIVE 7B: Reduce the use of tobacco and nicotine products by youth.
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