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	Did not participate
	Vikas Batra, MD, FACP, FC – Sussex Pulmonary & Endocrine Consultants, PA
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	Heather Bittner-Fagan, MD, MPH – Christiana Care Health System

	Did not participate
	Tiffany Edwards – Sussex County Health Coalition
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	Allison Gil, American Cancer Society

	Participated
	Stephen Grubbs, MD – American Society of Clinical Oncology
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	Sarah Hutton, EdD – Boys and Girls Club of Delaware

	Participated
	Nora Katurakes, RN, MSN, OCN – Christiana Care Health System 
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	Stephanie McClellan, MSN, RN, CMSRN – Bayhealth Medical Center
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	Lauren Moore, Tidal Health, Nanticoke

	Participated
	Sue Murray, DE Breast Cancer Coalition

	Participated
	Carolee Polek, RN, MSN, PhD – DE Diamond Chapter of the Oncology Nursing Society

	Did not participate
	Albert Rizzo, MD, FACP, FCCP – Christiana Care Health System

	Did not participate
	Robert Sikes, PhD. – University of Delaware

	Participated
	Sarah Toborowski – Quality Insights

	Did not participate
	Crystal Wright – Henrietta Johnson Medical Center

	Did not participate
	Michael R. Zaragoza, MD, FACS – Delaware Prostate Cancer Coalition

	
	

	Staff

	

	Participated
	Helen Arthur – Delaware Division of Public Health

	Participated
	Rosemary Doughten – Delaware Division of Public Health

	Participated
	Melissa Keiper – Delaware Division of Public Health

	
	

	Public/Guests
	

	Participated
	Suzanne Corson – Susan G. Komen

	Participated
	Robyn Biehm – Christiana Care Health System

	Participated
	Rita Williams – Beebe Healthcare

	Participated
	Lisa Gruss – Quality Insights

	
	


Welcome/Review/Approval of minutes



Review/Approval of Minutes
Chair, Dr. Heather Bittner-Fagan began the meeting at 10:05 am.  A motion was made by Dr. Stephen Grubbs to approve the October 2020 minutes and all participating approved the minutes as written.
Human papillomavirus (HPV) 5-year plan
Ms. Melissa Keiper, , Clinical Cancer Director, Division of Public Health (DPH) provided the HPV 5-year plan update for Mr. Jim Talbott, HPV Program Manager as he was unavailable due to working COVID-19 detail.  Ms. Keiper advised that headway is being made with the Department of Education (DOE) partnership, specifically increasing education on the importance of the HPV vaccine for boys and girls.  Regarding partnerships with insurance companies, some efforts have been stalled as a result of the pandemic.  Work is continuing with the State Innovation Committee and there is an ongoing contract with Quality Insights to increase providers’ knowledge and also to provide training regarding this initiative.  New media campaigns are waiting to be launched to be sure health care providers will be able to accommodate.  There was also an educational opportunity provided to the dental community.  Dr. Bittner-Fagan inquired if the HPV vaccine is routinely offered by school-based health centers.  One challenge identified at wellness centers includes lack of continuity of care, particularly since not all centers have access to Electronic Health Records (EHR).  Some wellness centers are still using a paper-based records system.  Additionally, parental consent is required for participation in wellness centers and can be a barrier to receiving care.  Additional barriers include form completion to receive the vaccine as well as are Medicaid and other insurance barriers.

Lung 5-year plan
Ms. Keiper provided an update of the Lung Cancer Screening Program 5-year plan.  The goals of the plan are:
	GOAL 1: Continue to promote lung cancer screening
	GOAL 2: Analyze Data in cancer screening databases
GOAL 3: Inform and educate health care providers and general public on available resources
	GOAL 4: Encourage healthy lifestyles and reduce risky behaviors
GOAL 5: Initiate and support policies and programs to reduce tobacco use and exposure to secondhand smoke
GOAL 6: Prevent initiation of tobacco, nicotine and emerging products use among youth and young adults
GOAL 7: Increase the number of Delawareans who stop using tobacco and nicotine products
Much discussion took place regarding how and what information is sent to the screening database.  It was suggested that a survey be created and sent to each lung cancer screening location to ask how information is gathered and what elements are missing.  Chair Dr. Bittner-Fagan asked Nora Katurakes to initiate an email to testing sites to inquire who is contact person and what is the clinical process for gathering information and submitting information, to ensure consistency in data elements that are submitted by all sites.  

Further discussion for Goal 2, #4 - Determine feasibility of developing and implementing a comprehensive cancer screening registry for Delaware.  Lung cancers should be reported to the American College of Radiology (ACR).  The Screening for Life Program continues to work with the ACR to determine reporting capabilities – warranted adding “revisit BRFSS guidelines now that the data has been released”.  Dr. Grubbs stated that data sets from both the ACR and BRFSS need to be continually analyzed. 

A question was posed as to how the DCC in collaboration with DPH would pay for additional patient navigators that are listed in Goal 1, #2 - Support Patient Navigators to support lung cancer screening.  Ms. Helen Arthur, Health Promotion Disease Prevention Section Chief, advised that there is no additional funding and that work is continuing with Delaware Hospital Association in gathering manpower to host patient navigation. Dr. Bittner-Fagan suggested removing part of the goal that aims to  look at additional resources to support nurse navigation.  Dr. Grubbs inquired if it is possible for Quality Insights to add additional sites for the health systems work, they are currently providing for lung cancer screening.  Ms. Sarah Toborowski from Quality Insights responded that they are recruiting five additional sites to increase lung cancer screening programs and rates.

DE Lung Cancer Screening Program
In 2015 the decision was made for the Screening for Life Program to reimburse providers for lung cancer screening for eligible clients. Originally the program provided screening for eligible clients for a duration of  three years.  In 2018 the Committee decided to extend the screening duration  for an additional two years for a total of five years.  At the end of the five-year period the data was to be reviewed.  Dr. Bittner-Fagan brought up the draft recommendations from United States Preventative Services Task Force (USPSTF).  Does the mortality benefit increase from the benefit of the program for 10 years?  There is benefit beyond five years.  Is there evidence to extend the screening for individuals to 10 years?  Dr. Grubbs stated that the data must be reviewed.  The recommendation for the top age limit is still 80 even if the program would allow lung cancer screening to continue.  This will be further discussed and finalized during the next committee meeting. 

Sharing Time
Ms. Suzanne Corson from Susan G. Komen shared information regarding the Komen Treatment Assistance Program.  It is available to all battling breast cancer that meet financial criteria.  The Program will be expanding in the next few months.  If anyone has any questions she can be contacted at scorson@komen.org and the website is https://www.s.komen.org/treatment-assistance-program/. 

Ms. Nora Katurakes from Christiana Care Health System inquired if the IMPACT group still meets.  She also requested information on the smoking quit rate and the number of people using the Quitline.  

Dr. Grubbs advised that the recommendations for colorectal cancer from the United States Preventative Services Task Force (USPSTF) are out for comment.  He thinks they are dropping the age to 45 but still waiting for the final recommendations.

Ms. Helen Arthur advised that the Cancer Risk Reduction committee received a presentation on flavored tobacco products during their meeting.  ED&P committee members were also interested in seeing the presentation.  It was proposed to offer it as a lunchtime presentation at the April 12, 2021 meeting.

Public Comment
No comments were made during this time.

Adjournment
The meeting was adjourned at 11:25 am.

Attachments



                               

Meeting documentation is available on the DCC website (www.healthydelaware.org) or by contacting Rosemary Doughten (Rosemary.Doughten@delaware.gov or 302-744-1000).
Future Meeting (s)




	Next Meeting:

Monday, April 12, 2021
Location - TBD

	Remaining 2021 meetings: 

Monday, July 12 
Monday, October 11 
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HPV 5 year plan

GOAL 2: Provide human papillomaviruses (HPV) vaccine to girls, young women, boys, and young men ages 9-26.

OBJECTIVE 2A: Conduct a multi-pronged approach targeting parents and physicians about the importance of the HPV vaccine for cancer prevention.

. e Data Source | Timeframe January 2021 Update
Task/Actions Party
Vear 1 and Ongoing. DPH attended the August 2020 DOE Nurses'
increasing education on the importance of HPV vaccination for boys and girls. ongoing and HPV updates and information.
c hio with the D . DI llaborate with Vear 1 and Ongoing. Reached out to the Department of Insurance
orm partners ‘|p with the Department o . nSl‘Jrance ( _) to C? abora .e Wi DPH and DOI MOuU . on 9/26/18 about Insurance providers promoting HPV
Insurance Providers to promote HPV Vaccinations to their medical providers. ongoing L
vaccinations.
Work with the State Innovation Committees to add the HPV vaccine discussion and Provider Year 1 and Ongoing. Activity: Reached out t_o Innovation Committee
. . . . DPH . on 6/1/2018, was referred to Elizabeth Brown, reached
distribution metrics to the provider scorecard statewide to measure change. scorecard ongoing
out to her on 9/27/18.
Provide training to medical providers on Quality Initiatives to increase providers Ongoing: Initial contract completed on 6/30/18. RFP has
knowledge on HPV vaccinations, communication techniques and vaccination coverage DPH Contract Year 1-2 been awareded to Quality Insights- contract extended
information to promote succssful administration of HPV vaccinations. through 6/30/2022
Provide training on the use of the Immunization Information System in order to view
and reconcile coverage rate data in the Immunization Information System for HPV DPH Contract Years 1-5 Ongoing: Contract is in place through 6/30/2022.

vaccinations.
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HPV 5 year plan

GOAL 2: Provide human papillomaviruses (HPV) vaccine to girls, young women, boys, and young men ages 9-26.

OBJECTIVE 2A: Conduct a multi-pronged approach targeting parents and physicians about the importance of the HPV vaccine for cancer prevention.

. e Data Source | Timeframe January 2021 Update
Task/Actions Party
Ongoing. A Request for proposal (RFP) has been
submitted, but with only one bidder. Bidder did not
meet the requirements. Program will be looking at
DPH Contract Years 1-5 | ) au! ; 'd'g h W , ne
Provide data entry services for providers to update their HPV vaccination data in the a ternatlye means of providing the service. Due to
Immunization Information System to arrive at a accurate coverage rate for HPV. pandemic, further efforts have been unable to be
undertaken.
. _ . . . . DPH and Ongoing. Strategic plan to inform awareness, education,
7 Dlsse.rr.nnate mess.ages statewide using tra.ckal.ole media tactics t? both parents and c Evaluation Years 1-2 and outreach efforts are underway. Plan to launch in
physicians on the importance of HPV vaccination for boys and girls ages 9-26. ontractor Janaury 2019. Media campaign intitiated in 2019.
Ongoing. Evaluation conducted at the end of campaign
eriod. Using FB newsfeed ads, 41K people reached
Conduct an evaluation of media tactics to determine the effectiveness, and refine as P . g . . P p.
Trackable delivering 623 clicks and 477 website
8 |needed based on results. DPH ) Years 2-3 . )
media visits. The banner ads were very successful spreading
awareness, delivering over 2M impressions and over
5K clicks. The banners drove 3,599 website sessions.
Provide workflow assessments to immunization providers to ensure correct . . . I
) . Ongoing. Program will reach out to determine feasibility
9 |recommendation of HPV at each office visit. DPH Contract Year 2
of the assessment. Contract to conclude 6/30/2022
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HPV 5 year plan

GOAL 2: Provide human papillomaviruses (HPV) vaccine to girls, young women, boys, and young men ages 9-26.

OBJECTIVE 2A: Conduct a multi-pronged approach targeting parents and physicians about the importance of the HPV vaccine for cancer prevention.

Responsible

Data Source | Timeframe January 2021 Update
Task/Actions Party
1st Champion has been nominated, package e-mailed to
Promote the HPV Vaccine is Cancer Prevention Champion Award program will serve Trackable the CDC on 9/4/2018, nomination package went out to
to motivate clinicians to adopt effective recommendation practices, and help educate DPH website Year 2 qualified providers in 2019 but no responses were
clinicians on the individual- and practice-level changes that can improve HPV engagement submitted to the program. The program will continue to
vaccination rates. The program also serves reinforcement for parental audiences that send out HPV Champion Information to eligible providers
HPV vaccination is an important part of cancer prevention and a normal part of yearly.
adolescent immunization.
Provide education opportunities to Dental community concerning HPV, to include Completed. Reached out to Dental Director and Dental
screening, surveillance, and immunization. DPH Contract Year 2 Society of Delaware. Research to determine educational
needs of Dental community.
. . . State . Ongoing. Activity: Reached out to Innovation Committee
Evaluate the provider scorecard to determine effectiveness. Innovation Provider Year 5 on 6/1/2018, was referred to Elizabeth Brown, reached
) scorecard
Committee out to her on 9/27/18.
Completed: Reached out to Coalition on 9/19/18 to host
DPH and meeting on vaccine recommendations for college entry
Arrive at a consensus with Colleges and Universities on making HPV a Immunization Evaluation Years 2-3 with colleges and universities in Delaware. Kate Smith
recommended/required vaccination for college entry Coalition of reached out to 2 Colleges and Universities. There was
Delaware little interest from these colleges/universities to meet.

No current activities due to COVID 19.
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OBJECTIVE 1A Decrease the number of late stage lung cancer diagnoses by 20%

Lung 5 year plan

GOAL 1: Continue to promote lung cancer screening
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Task/Actions Responsible Party Data Source Timeframe January 2021 Update
Determine baseline number of late stage lung cancers diagnosed. DPH DCR Year 1 Done. Out of 3,965 lung cancers diagnosed, 2942 (73.7%) are late stage (regional and distant combined). 847 are local, and 194 are unknown.
ED&P Committee and Ongoing. Statewide lung navigators are in place at Christiana Care and Bayhealth. Work is needed to determine if additional lung patient navigators
Support Patient Navigators to support lung cancer screening. DPH Contracts Year 1 are needed.
Screening for Life
Provider
Maintain current and establish new relationships with primary care providers to Agreement,
increase screening rates for Medicare patients. DPH and Navigators Screening Rates [Year 1-5 Ongoing. Agreements in place with 4 provider sites. Aim to recruit up to three additional provider sites.
4|Enhance relationships with Medicaid and FQHCs to increase screening rates. DPH Organization Data |Year 1-5 Ongoing. Quality Insights is activly pursuing one FQHC to initiate Academic Detailing program for providers and patient navigators at this site.
Cancer Incidence
Increase the number of screenings performed in areas where late stage lung and Mortality
5[cancers are more predominately diagnosed. Navigators and DPH Data Year 1-5 Ongoing. Additional data analysis is needed to identify gaps and barriers in screening.
National Lung The US Preventive Services Task Force (USPSTF) issued draft guidelines July 2020. Draft recommendations expand screening eligibility to include
Explore expanding lung cancer screenings to those with occupational exposure Cancer Screening annual screening with low-dose CT in adults ages 50 - 80 who have a 20 pack year smoking history and who currently smoke or have quit smoking
and/or those exposed to second hand smoke. DCC Guidelines Year 5 within the past 15 years. This is a "B" recommendation. Final determination of adaptation of these guidlines is pending a final decision by the USPSTF.
OBIJECTIVE 1B: Reimburse lung cancer screening for Delawareans who meet age and income eligibility guidelines.
Task/Actions Responsible Party Data Source Timeframe January 2021 Update
Continue annual allocation for lung cancer screening for men and women Year 1 and
ineligible for federal funded screening. General Assembly State Budget ongoing Ongoing.
Reimburse providers through the Screening for Life program for services for lung State and Federal |Year 1 and
cancer screening for men and women DPH Budget ongoing Ongoing.
GOAL 2: Analyze Data in cancer screening databases
OBJECTIVE 2A: Review available data.
Task/Actions Responsible Party Data Source Timeframe |January 2021 Update
Review data elements available in the Screening for Life Database and Delaware
Lung Cancer Registry. DPH Database Year 1 Ongoing.
Expand and modify current database used to track screening activity in the SFL Year 2 and
program and update as necessary. DPH, Contractor Database ongoing Done. New Screening for Life database was placed into production July, 2020.
Evaluate screening data in both the SFL program and the Delaware Lung Cancer Year 1 and
Registry. DPH Screening data ongoing Ongoing.
Determine feasibility of developing and implementing a comprehensive cancer Lung cancers should be reported to the American College of Radiology. The Screening for Life program continues to work with the ACR to determine
screening registry for Delaware. ED&P Committee Year 5 reporting capabilities.

GOAL 3: Inform and educate health care providers and general public on available resources.
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Lung 5 year plan

OBJECTIVE 3A: Develop and implement evidence based education campaigns.

Task/Actions Responsible Party Data Source Timeframe [January 2021 Update
Ongoing. An analysis was recently performed to identify potential gaps in current marketing efforts. This information will be used to inform new
Promote campaigns to public and businesses focusing on available resources. Year 1 and campaigns and marketing efforts. Additional information is being gathered to determine effectiveness of screening campaign in light of on-going
DPH, Contractor Campaign ongoing pandemic.
Provide updates to health care professionals through letters and personal Year 1 and Ongoing. Lung navigators conduct outreach to providers offices. Updates are sent to providers via newsletters. Academic detailing program will
outreach. DPH, Contractor Letters ongoing continue to be deployed to interested providers.

GOAL 4:

Encourage healthy lifestyles and reduce risky behaviors

OBJECTIVE 4A: Develop, implement and evaluate social marketing campaigns to support tobacco free living

Task/Actions Responsible Party Data Source Timeframe [January 2021 Update
DHSS tobacco program
staff, IMPACT members, Ongoing. Print ads, radio ads and social media ads were developed to let individuals know that smokers are at an increased risk of severe illness from
Increase awareness of available cessation programs and resources. DCC ATS, Quitline Ongoing COVID-19.
DHSS tobacco program
staff, IMPACT members,
Increase awareness of problems associated with secondhand smoke. DCC ATS, YTS, BRFSS  |Ongoing Ongoing. Ongoing education on second hand smoke via television commercial and social media.
Use "counter-marketing" to decrease the effectiveness of tobacco industry DHSS tobacco program
promotions and to increase knowledge of harmful effects of tobacco and nicotine [staff, IMPACT members, Ongoing. Print ads, radio ads and social media ads were developed to let people know that smokers are at an increased risk of severe illness from
use. DCC ATS, YTS Ongoing COVID-19.
OBJECTIVE 4B: Educate the public about ways to lower their cancer risks.
Task/Actions Responsible Party Data Source Timeframe |January 2021 Update
Increase the percentage of health care practioners (including ob-gyns and
pediatricians) who inquire about secondhand smoke exposure in homes and DPH Tobacco program
vehicles and who counsel patients and their families regarding the dangers of staff, IMPACT members, |Physician Survey, In the fall 2018, 28 home visitors were trained on home health hazards (including secondhand smoke) and cessation resources including the Delaware
secondhand smoke. DCC BRFSS, ATS, YTS |Ongoing Quitline.
DPH Tobacco Prevention
Program, Maternal &
Develop partnerships with the Department of Education as well as various Child Health, Health
programs across DPH to increase awareness of the problems associated with Equity and Northern and Year 1 and Vape toolkit (vapefreede.com) was developed in partnership with DOE, Kids Department and Polytech. Toolkit includes downloadable fact sheets,
secondhand smoke. Southern Health Services [BRFSS, YTS ongoing curriculums, links to other resources(including smoke free policies and other education on secondhand smoke) and a social media calendar kit.
OBJECTIVE 4C: Increase the number of people who don't allow smoking in their homes or vehicles.
Task/Actions Responsible Party Data Source Timeframe January 2021 Update
Disseminate information about the harmful effects of tobacco and vape smoke to Ongoing. A commercial which informs the public that some vape pods can contain as much nicotine as a pack of cigarettes airs on television and social
consumers and vulnerable populations through targeted multimedia campaigns |DPH, Voluntary heath Media tracker, media outlets used by youth and young adults. Vape toolkit (vapefreede.com) was developed in partnership with DOE, Kids Department and Polytech.
and community outreach. organizations ATS, BRFSS Ongoing Toolkit includes downloadable fact sheets, curriculums, policies, links to other resources and a social media calendar kit.
Educate health practioners through professional associations on the value of DPH, Voluntary heath
preventing exposure to secondhand smoke, including vapor emissions. organizations, IMPACT  |Physician Survey |Ongoing Ongoing

GOAL 5: Initi

ate and support policies and programs to reduce tobacco use and exposure to secondhand smoke.

OBJECTIVE 5A: Increase excise tax on tobacco products.

Task/Actions Responsible Party Data Source Timeframe January 2021 Update
Educate and inform legislators and decision makers on the health and economic [Voluntary health

benefits of increasing the state excise tax on tobacco products and having a tax  |organizations, IMPACT, |Legislation

on e-cigarettes. DCC tracker Ongoing Ongoing
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Lung 5 year plan

Educate and inform the general public on the many health and economic benefits [Voluntary health
of increasing the state excise tax on tobacco products and having a tax on e- organizations, IMPACT,
cigarettes. DCC ATS Ongoing Ongoing
Voluntary health Legislation
Introduce and pass legislation to increase the excise tax on tobacco products. organizations, legislature |tracker Ongoing Excise tax was increased in 2017.
Voluntary health Legislation
Introduce and pass legislation to tax e-cigarettes. organizations, legislature |tracker Ongoing E-cigarettes have been taxed since 2017.
OBJECTIVE 5B: Sustain and enforce Delaware's Clean Indoor Air Act (CIAA)
Task/Actions Responsible Party Data Source Timeframe January 2021 Update
Voluntary health
organizations, IMPACT, (Legislation Ongoing. Senate Substitute 1 for Senate Bill 25, was passed and raised the age of sale of tobacco products to 21 years (effective July 16, 2019). It also
Monitor draft legislation for any potential changes to CIAA. DCC, DHSS tracker Ongoing amended the CIAA to prohibit individuals under 21 from entering vapor establishments.
Enforce laws pertaining to secondhand smoke from vape products. DPH CIAA log Ongoing Ongoing. DPH created new signs for vapor establishments to post regarding the change in law that individuals under 21 are not allowed to enter.
OBJECTIVE 5C: Increase insurance coverage for cessation.
Task/Actions Responsible Party Data Source Timeframe January 2021 Update
Voluntary health Quitline, ATS,
Work with public (Medicaid) and private insurance, unions and employers to organizations, IMPACT, |Insurance plan
cover cessation counseling and products. DCC, DHSS data Ongoing Ongoing. Medicaid currently reimburses DPH partially for Medicaid clients that use the Quitline.
OBJECTIVE 5D: Support National and Delaware tobacco policy initiatives.
Task/Actions Responsible Party Data Source Timeframe January 2021 Update
Voluntary health
Work with public (Medicaid) and private insurance, unions and employers to organizations, IMPACT, |Insurance
cover cessation counseling and products. DCC, DHSS records, ATS Ongoing Ongoing. Medicaid currently reimburses DPH partially for Medicaid clients that use the Quitline.
Continue to recommend funding from Delaware Health Fund for tobacco DHFAC
prevention activities. DCC, IMPACT recommendation |Annually The DHFAC recommended level funding for tobacco prevention activities for FY22.
Identify potential funding opportunities to support tobacco prevention efforts Total amount of
from private and federal sources. DHSS, IMPACT funding Ongoing Ongoing
Enact legislation to increase the age to 21 to purchase cigarettes and other Voluntary health Legislation
tobacco products. organizations, legislature |tracker Year 2 Legislation (Senate Substitute 1 for Senate Bill 25) was introduced and passed that increased the age of sale to 21. This went into effect July 16, 2019.
Voluntary health Legislation Year 2 and
Increase the cost of retail business license to sell tobacco from the current $5. organizations, legislature |tracker ongoing HB242 was passed in 2017. This raised the cost of license to $50 (including vape store owners).
Voluntary health Legislation Year 2 and
Enact legislation to require vapor establishments to have tobacco sale licenses.  |organizations, legislature |tracker ongoing HB242 was passed in 2017. Vapor establishments are now required to have tobacco retailer licenses.
Voluntary health
Support development of policies by agencies who are responsible for individuals [organizations, IMPACT,
under their jurisdiction. DCC, DHSS Survey data Ongoing Ongoing
Provide tobacco plan to agencies and organizations and partner with them to
achieve objectives. DHSS, IMPACT, DCC Program records |Ongoing Ongoing
Review and update Tobacco Plan IMPACT, DHSS Program records |Year 1 The tobacco plan was updated in 2017. The next update is planned for 2022.
OBJECTIVE 5E: Reduce exposure to secondhand smoke in outdoor areas.
Task/Actions Responsible Party Data Source |Timeframe January 2021 Update
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Lung 5 year plan

Support development of policies to not allow smoking near entrances or exits to

Voluntary health
organizations, IMPACT,

Program records,

buildings. DCC, DHSS mini grants Ongoing Ongoing
Voluntary health
Support health care facilities, workplaces, agencies and municipalities to develop [organizations, IMPACT,
smoke-free grounds policies. DCC, DHSS Survey data Ongoing Ongoing. Through mini grants have provided support for municipalities as they go smoke free. Includes providing funds for signage.
OBIJECTIVE 5F: Explore potential policies to reduce children’s exposure to secondhand smoke.
Task/Actions Responsible Party Data Source Timeframe January 2021 Update
Identify new locations, including multi-housing units that will adopt no-smoking  |Voluntary health
policies. organizations, IMPACT |Survey data Ongoing Ongoing
Increase the percentage of health care practitioners who inquire about Voluntary health Survey data,
secondhand smoke exposure in homes and who counsel patients and their organizations, IMPACT, |provider
families. DCC, DHSS scorecard Ongoing Ongoing provider education.

GOAL 6: Prevent initiation of tobacco, nicotine and emerging products use among youth and young adults.

OBJECTIVE 6A: Fund youth and young adult tobacco prevention programs.

Task/Actions Responsible Party Data Source Timeframe January 2021 Update
Implement evidence-based tobacco prevention programs for schools and DHSS tobacco program  |Program records, Ongoing provision of mini grants and funding of youth led activities such as Kick Butts Generation. DPH has assisted some schools with implementing
communities. staff, IMPACT members, |YTS Ongoing Botvin Lifeskills curriculum which includes traditional tobacco use prevention as well as e-cigarettes.

DHSS tobacco program
Conduct programs in colleges and workplaces that target young adults. staff, IMPACT members |Program records |[Ongoing Ongoing. Delawareans Against Nicotine and Tobacco Exposure is a coalition of young adults active on various college campuses in Delaware.
Enforce Delaware tobacco Regulation 877, which prohibits the use and School profile
distribution of tobacco products by all staff, students, visitors and parents in reports
school buildings, on school grounds in school leased or owned vehicles and (violations
property and all school affiliated functions, on and off school grounds. DOE, IMPACT members |recorded) Ongoing Ongoing

DCC, Voluntary health Surveys, focus

organizations, DPH groups, trackable |Year 1 and Ongoing- Youth Tobacco Survey, focus groups etc. American Lung Activities (Kick Butts Generation/FORCE, DANTE) are evaluated by a subcontract
Ensure evaluation is conducted on all programs and activities. Cancer Program media ongoing Public Health Management Consultants.

GOAL 7: Increase the a

mount of Delawareans who stop using tobacco and nicotine products.

OBJECTIVE 7A: Enhance available resources to help people quit use of tobacco and nicotine products.

Task/Actions Responsible Party Data Source Timeframe January 2021 Update

DPH tobacco program Ongoing. During Fiscal Year 2020, the Delaware QuitLine received 7434 calls with 2108 individuals receiving cessation counseling by phone and 571
Provide qualified counseling services (Quitline/face-to-face). staff Quitline Ongoing registrants to receive face-to-face counseling.

DPH tobacco program Quitline, web Ongoing. Coaching provided through QuitSupport.com. Information also provided at HealthyDelaware.org. The new online vape tool kit will include
Provide online information and resources. staff reports Ongoing resources for quitting vaping.

DPH tobacco program
Provide approved cessation products to program recipients. staff Quitline Ongoing Ongoing- Quitline provides all seven FDA approved cessation aids free of charge to participants.
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DCC, Voluntary health

Surveys, focus

organizations, DPH groups, trackable [Year 1 and
4|Ensure evaluation is conducted on all programs and activities. Cancer Program media, Quitline |ongoing Ongoing: Adult Tobacco Survey, Quitline participant survey postcard, Quit rates (@34%).
OBIJECTIVE 7B: Reduce the use of tobacco and nicotine products by youth.
Task/Actions Responsible Party Data Source Timeframe January 2021 Update
1|Provide cessation programs specific to youth and young adults. DPH tobacco program ATS, YTS Ongoing Ongoing. Not on Tobacco Use (NOT) has been enhanced to include e-cigarettes.
DPH tobacco program The Delaware Quitline lowered age requirements to allow those under age 18 to use services. Indviduals aged 13 - 17 are able to utilize the Quitline's
2[Expand current programs to include youth. staff YTS Ongoing phone counseling and online services. This change went into effect in November, 2019.

Page 5 of 5







image1.png
DELAWARE
CANCER

CONSORTIUM




image2.png
DELAWARE
CANCER

CONSORTIUM




